## Tasks List - R1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner | Iteration
1 | 05. Payment Processing | 05. 01 | Net Banking | Implement GUI based changes to site | 2020-10-09 | 2020-10-11 | 100% | Prathmesh | I2
2 | 05. Payment Processing | 05. 01 | Net Banking | Add back-end support to functions | 2020-10-11 | 2020-10-12 | 100% | Hari | I2 | Iteration 1
3 | 05. Payment Processing | 05. 01 | Net Banking | Confirm database support | 2020-10-12 | 2020-10-12 | 100% | Khalid | I2 | Iteration 2
4 | 05. Payment Processing | 05. 01 | Net Banking | Assign Test cases for the core features | 2020-10-12 | 2020-10-12 | 100% | Bhakti | I2
5 | 05. Payment Processing | 05. 01 | Net Banking | Test Entitlements | 2020-10-13 | 2020-10-13 | 100% | Aditya Adhuri | I2
6 | 05. Payment Processing | 05. 01 | Net Banking | Test Field validations for all fields | 2020-10-13 | 2020-10-13 | 100% | Aditya Adhuri | I2
7 | 05. Payment Processing | 05. 01 | Net Banking | Test Data dependency validation | 2020-10-13 | 2020-10-13 | 100% | Soham Save | I2
8 | 05. Payment Processing | 05. 01 | Net Banking | Acceptance Test on Qtest | 2020-10-14 | 2020-10-14 | 100% | ALL | I2
9 | 05. Payment Processing | 05. 01 | Net Banking | Create Test execution log | 2020-10-15 | 2020-10-15 | 100% | Kuntal | I2
10 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Implement GUI based changes to site | 2020-09-18 | 2020-09-19 | 100% | Prathmesh | I1
11 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Add back-end support to functions | 2020-09-20 | 2020-09-21 | 100% | Hari | I1
12 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Confirm database support | 2020-09-21 | 2020-09-21 | 100% | Khalid | I1
13 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Assign Test cases for the core features | 2020-09-22 | 2020-09-22 | 100% | Bhakti | I1
14 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Test Entitlements | 2020-09-22 | 2020-09-23 | 100% | Aditya Adhuri | I1
15 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Test Field validations for all fields | 2020-09-23 | 2020-09-23 | 100% | Aditya Adhuri | I1
16 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Test Data dependency validation | 2020-09-23 | 2020-09-23 | 100% | Soham Save | I1
17 | 05. Payment Processing | 05. 02 | Credit / Debit Card | Create Test execution log | 2020-09-23 | 2020-09-23 | 100% | Kuntal | I1
18 | 05. Payment Processing | 05. 03 | Paypal | Implement GUI based changes to site | 2020-09-25 | 2020-09-26 | 100% | Prathmesh | I1
19 | 05. Payment Processing | 05. 03 | Paypal | Add back-end support to functions | 2020-09-27 | 2020-09-28 | 100% | Hari | I1
20 | 05. Payment Processing | 05. 03 | Paypal | Confirm database support | 2020-09-28 | 2020-09-28 | 100% | Khalid | I1
21 | 05. Payment Processing | 05. 03 | Paypal | Assign Test cases for the core features | 2020-09-28 | 2020-09-28 | 100% | Bhakti | I1
22 | 05. Payment Processing | 05. 03 | Paypal | Test Entitlements | 2020-09-28 | 2020-09-29 | 100% | Aditya Adhuri | I1
23 | 05. Payment Processing | 05. 03 | Paypal | Test Field validations for all fields | 2020-09-29 | 2020-09-29 | 100% | Aditya Adhuri | I1
24 | 05. Payment Processing | 05. 03 | Paypal | Test Data dependency validation | 2020-09-29 | 2020-09-30 | 100% | Soham Save | I1
25 | 05. Payment Processing | 05. 03 | Paypal | Test Data Flow Out | 2020-09-30 | 2020-09-30 | 100% | Soham Save | I1
26 | 05. Payment Processing | 05. 03 | Paypal | Create Test execution log | 2020-09-30 | 2020-09-30 | 100% | Kuntal | I1
27 | 07. Database | 07. 01 | User's information | Create mysql database for user's information | 2020-10-16 | 2020-10-16 | 100% | Prathmesh | I2
28 | 07. Database | 07. 01 | User's information | Add back-end support and database connectivity | 2020-10-17 | 2020-10-17 | 100% | Hari | I2
29 | 07. Database | 07. 01 | User's information | Confirm database support | 2020-10-18 | 2020-10-18 | 100% | Khalid | I2
30 | 07. Database | 07. 01 | User's information | Assign Test cases for the core features | 2020-10-18 | 2020-10-18 | 100% | Bhakti | I2
31 | 07. Database | 07. 01 | User's information | Test Core Functionality + Data Flow in | 2020-10-19 | 2020-10-19 | 100% | Aditya Adhuri | I2
32 | 07. Database | 07. 01 | User's information | Test Core Functionality + Data Flow out | 2020-10-19 | 2020-10-20 | 100% | Aditya Adhuri | I2
33 | 07. Database | 07. 01 | User's information | Test Entitlements | 2020-10-20 | 2020-10-20 | 100% | Soham Save | I2
34 | 07. Database | 07. 01 | User's information | Acceptance Test on Qtest | 2020-10-20 | 2020-10-21 | 100% | ALL | I2
35 | 07. Database | 07. 01 | User's information | Create Test execution log | 2020-10-21 | 2020-10-21 | 100% | Soham Save | I2
36 | 07. Database | 07. 02 | Sitter's information | Create mysql database for sitter's information | 2020-10-16 | 2020-10-16 | 100% | Prathmesh | I2
37 | 07. Database | 07. 02 | Sitter's information | Add back-end support and database connectivity | 2020-10-17 | 2020-10-17 | 100% | Hari | I2
38 | 07. Database | 07. 02 | Sitter's information | Confirm database support | 2020-10-18 | 2020-10-18 | 100% | Khalid | I2
39 | 07. Database | 07. 02 | Sitter's information | Assign Test cases for the core features | 2020-10-18 | 2020-10-18 | 100% | Bhakti | I2
40 | 07. Database | 07. 02 | Sitter's information | Test Core Functionality + Data Flow out | 2020-10-19 | 2020-10-19 | 100% | Aditya Adhuri | I2
41 | 07. Database | 07. 02 | Sitter's information | Test Entitlements | 2020-10-21 | 2020-10-21 | 100% | Soham Save | I2
42 | 07. Database | 07. 02 | Sitter's information | Acceptance Test on Qtest | 2020-10-21 | 2020-10-22 | 100% | ALL | I2
43 | 07. Database | 07. 02 | Sitter's information | Create Test execution log | 2020-10-21 | 2020-10-21 | 100% | Kuntal | I2
45 | 07. Database | 07. 03 | Transaction information | Create mysql database for transaction information | 2020-10-16 | 2020-10-16 | 100% | Prathmesh | I2
46 | 07. Database | 07. 03 | Transaction information | Add back-end support and database connectivity | 2020-10-17 | 2020-10-17 | 100% | Prathmesh | I2
47 | 07. Database | 07. 03 | Transaction information | Confirm database support | 2020-10-18 | 2020-10-18 | 100% | Khalid | I2
48 | 07. Database | 07. 03 | Transaction information | Assign Test cases for the core features | 2020-10-18 | 2020-10-18 | 100% | Bhakti | I2
49 | 07. Database | 07. 03 | Transaction information | Test Core Functionality + Data Flow in | 2020-10-20 | 2020-10-21 | 100% | Aditya Adhuri | I2
50 | 07. Database | 07. 03 | Transaction information | Test Core Functionality + Data Flow out | 2020-10-21 | 2020-10-21 | 100% | Aditya Adhuri | I2
51 | 07. Database | 07. 03 | Transaction information | Test Entitlements | 2020-10-22 | 2020-10-22 | 100% | Soham Save | I2
52 | 07. Database | 07. 03 | Transaction information | Acceptance Test on Qtest | 2020-10-22 | 2020-10-22 | 100% | ALL | I2
53 | 07. Database | 07. 03 | Transaction information | Create Test execution log | 2020-10-22 | 2020-10-22 | 100% | Kuntal | I2