## Working Plan
Color Coding |  | Completed |  |  |  | SPRING 2020 SEMESTER
In Progress
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-03-31 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-04-28 | 2020-05-05
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress
Project Initiation | Confirm Project Team Roles | ALL | 2020-01-28 | 2020-01-28 | 100%
| Discuss Project Proposals | ALL | 2020-01-31 | 2020-02-04 | 100%
| Develop two business cases | Kuntal Surwade | 2020-01-31 | 2020-02-04 | 100%
| Develop Project Initiation Document (PID) | Kuntal Surwade | 2020-02-07 | 2020-02-11 | 100%
| Produce initial Project Plan, RACI | Kuntal Surwade | 2020-02-14 | 2020-02-18 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Analysis | Produce BRM diagram, define User Roles | Harivatsav S. R, | 2020-02-20 | 2020-02-25 | 100%
| Produce Context Diagram, Define System Interfaces | Bhakti Shastri | 2020-02-20 | 2020-02-25 | 100%
| Agree to System Requirements types | Bhakti Shastri | 2020-02-20 | 2020-02-25 | 100%
| Business Requirements | Harivatsav S. R, | 2020-02-27 | 2020-03-03 | 100%
| Define Functional Decomposition, Fishbone Diagrams | Bhakti Shastri | 2020-02-27 | 2020-03-03 | 100%
| Produce RCT document | Bhakti Shastri | 2020-02-27 | 2020-03-03 | 100%
| Selecting RCT Features to implement | Kuntal, Harivatsav | 2020-03-05 | 2020-03-10 | 100%
| Produce analysis diagrams (UML, DFD) | Bhakti Shastri | 2020-03-05 | 2020-03-10 | 100%
| Define functional requirements (User Stories) | Bhakti Shastri | 2020-03-05 | 2020-03-10 | 100%
| Update Project Plan with additional requirements tasks | Kuntal Surwade | 2020-03-05 | 2020-03-10 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
High Level Design | ER Diagram (Conceptual and Logical) | Khalid Francis | 2020-03-26 | 2020-03-31 | 0%
| Database Design ( Table spec) | Khalid Francis | 2020-03-26 | 2020-03-31 | 0%
| Dataflow Diagram(Physical) | Bhakti Shastri | 2020-03-26 | 2020-03-31 | 0%
| Architecture Diagrams | Prathmesh, Khalid | 2020-04-02 | 2020-04-07 | 0%
MILESTONE 3: DESIGN COMPLETED
Implementation | Class Diagrams | Prathmesh Pathak | 2020-04-09 | 2020-04-14 | 0%
| Sequence Diagrams | Prathmesh Pathak | 2020-04-09 | 2020-04-14 | 0%
| Updated Project Plan | Kuntal Surwade | 2020-04-09 | 2020-04-14 | 0%
| Coding & Implemenation | Prathmesh Pathak | 2020-04-09 | 2020-04-14 | 0%
MILESTONE 4: CODING COMPLETED
Testing | Plan testing, produce a Test Plan document | Soham Save | 2020-04-16 | 2020-04-21 | 0%
| Evaluate Features to be Tested | Soham Save | 2020-04-16 | 2020-04-21 | 0%
| Design Test Cases | Aditya Aduri | 2020-04-16 | 2020-04-21 | 0%
| Execute Test Cases | Aditya Aduri | 2020-04-16 | 2020-04-21 | 0%
| Anaylze Test Results | ALL | 2020-04-16 | 2020-04-21 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2020-04-29 | 2020-05-05 | 0%

## Initial Plan
Color Coding |  | Completed |  |  | SPRING 2020 SEMESTER
In Progress
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-03-31 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-04-28 | 2020-05-05
Project Phase | Activity | Task Owner Name | Start Date | End Date
Project Initiation | Confirm Project Team Roles | ALL | 2020-01-28 | 2020-01-28
| Discuss Project Proposals | ALL | 2020-01-31 | 2020-02-04
| Develop two business cases | Kuntal Surwade | 2020-01-31 | 2020-02-04
| Develop Project Initiation Document (PID) | Kuntal Surwade | 2020-02-07 | 2020-02-11
| Produce initial Project Plan, RACI | Kuntal Surwade | 2020-02-14 | 2020-02-18
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Analysis | Produce BRM diagram, define User Roles | Harivatsav S. R, | 2020-02-20 | 2020-02-25
| Produce Context Diagram, Define System Interfaces | Bhakti Shastri | 2020-02-20 | 2020-02-25
| Agree to System Requirements types | Bhakti Shastri | 2020-02-20 | 2020-02-25
| Business Requirements | Harivatsav S. R, | 2020-02-27 | 2020-03-03
| Define Functional Decomposition, Fishbone Diagrams | Bhakti Shastri | 2020-02-27 | 2020-03-03
| Produce RCT document | Bhakti Shastri | 2020-02-27 | 2020-03-03
| Selecting RCT Features to implement | Kuntal, Harivatsav | 2020-03-05 | 2020-03-10
| Produce analysis diagrams (UML, DFD) | Bhakti Shastri | 2020-03-05 | 2020-03-10
| Define functional requirements (User Stories) | Bhakti Shastri | 2020-03-05 | 2020-03-10
| Update Project Plan with additional requirements tasks | Kuntal Surwade | 2020-03-05 | 2020-03-10
MILESTONE 2: REQUIREMENTS COMPLETED
High Level Design | ER Diagram (Conceptual and Logical) | Khalid Francis | 2020-03-26 | 2020-03-31
| Database Design ( Table spec) | Khalid Francis | 2020-03-26 | 2020-03-31
| Dataflow Diagram(Physical) | Bhakti Shastri | 2020-03-26 | 2020-03-31
| Architecture Diagrams | Prathmesh, Khalid | 2020-04-02 | 2020-04-07
MILESTONE 3: DESIGN COMPLETED
Implementation | Class Diagrams | Prathmesh Pathak | 2020-04-09 | 2020-04-14
| Sequence Diagrams | Prathmesh Pathak | 2020-04-09 | 2020-04-14
| Updated Project Plan | Kuntal Surwade | 2020-04-09 | 2020-04-14
| Coding & Implemenation | Prathmesh Pathak | 2020-04-09 | 2020-04-14
MILESTONE 4: CODING COMPLETED
Testing | Plan testing, produce a Test Plan document | Soham Save | 2020-04-16 | 2020-04-21
| Evaluate Features to be Tested | Soham Save | 2020-04-16 | 2020-04-21
| Design Test Cases | Aditya Aduri | 2020-04-16 | 2020-04-21
| Execute Test Cases | Aditya Aduri | 2020-04-16 | 2020-04-21
| Anaylze Test Results | ALL | 2020-04-16 | 2020-04-21
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2020-04-29 | 2020-05-05