## Road Map
Pet-a-Dog
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/02/20 | Iteration 2 - 10/23/20 | Iteration 3 - 11/06/20 | Iteration 4 - 12/04/20
Module 1 - Home | 01.01 Guest User | 3
| 01.02 Subscribed User | 4
Module 2 - Booking Module | 02.01 Searching a Sitter | 4
| 02.02 Selecting a type of service | 3 |  |  | x
| 02.03 Booking a Sitter | 3
Module 3 - Tips and Tricks | 03.01 Selecting the breed of the dog | 4
| 03.02 Selecting the measurements | 4
| 03.03 Housing Conditions | 3
Module 4 - Sitter Monitoring | 04.01 Accessing Sitters location | 4 |  |  |  | x
| 04.02 Estimated Time of Arrival | 4 |  |  |  | x
Module 5 - Payment Processing | 05.01 Netbanking | 4 | x
| 05.02 Credit / Debit Card | 4 | x
| 05.03 Paypal | 4 | x
Module 6 - Reviews | 06.01 Feedback | 4 |  |  | x
| 06.02 Comment | 4 |  |  | x
Module 7 - Database | 07.01 User's Information | 4 |  | x
| 07.02 Sitter's information | 3 |  | x
| 07.03 Transaction information | 4 |  | x
|  | VELOCITY: | 12 | 11 | 11 | 8

## Story Map
Epics |  | Pet-a-Dog - User Story Map
Epic 1 - Home |  | Epic 1 - Home | Epic 2 - Booking Module | Epic 3 - Tips and Tricks | Epic 4 - Sitter Monitoring | Epic 5 - Payment Processing | Epic 6 - Review | Epic 7 - Database
Epic 2 - Booking Module | User Stories |  |  |  |  | 05.01 Netbanking
Epic 3 - Tips and Tricks | [5 empty] | 05.02 Credit / Debit Card
Epic 4 - Sitter Monitoring | [5 empty] | 05.03 Paypal |  |  | Iteration 1
Epic 5 - Payment Processing | [7 empty] | 07.01 User's Information
Epic 6 - Review | [7 empty] | 07.02 Sitter's information
Epic 7 - Database | [7 empty] | 07.03 Transaction information | Iteration 2
|  |  | 02.02 Selecting a type of service |  |  |  | 06.01 Feedback
[7 empty] | 06.02 Comment |  | Iteration 3
04.01 Accessing Sitters location
04.02 Estimated Time of Arrival
Iteration 4